## Plan
Plan ID | Plan name | Date of export
mpbv05eogkCmO9sK4CoVV2QAEJ1N | Test Template | 2026-10-07

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
ts_u89-E4UioP7O4TbgE7WQANQft | Create Project Charter | Planning |  | Not started | Urgent | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-09 | 2026-09-29 |  | false
eI9R31SgOUyOfKsRr9BGsGQABWKX | Kickoff Meeting | Planning |  | Not started | Important |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-12 | 2026-11-12 |  | false |  |  | 0/1 | Deck generated
GnwBOY2jjkq32Fy2GaUWLGQAOxte | Architecture Diagram | Design |  | Not started | Medium | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-09 | 2026-10-07 |  | false |  |  | 0/3 | Final Review;Initial Draft;Comments Resolved
VUaPEzB-YkmOlP5sZO8I3GQAAIp- | Final Readiness Review | Deployment |  | In progress | Medium | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-04 | 2026-11-07 |  | false
4aCd4U-ChEGCJnnDmQodR2QAEWxW | Identify Stakeholders | Planning |  | In progress | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-08 | 2026-09-27 |  | false
NX40UYKHtEiv71JIbz-EIGQAAgGz | Define Scope | Planning |  | Completed | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-10 |  |  | false | 2026-10-07 | Emma Plimpton Liebowitz
3bzYQ5cZjEKjVbU74Swle2QAG3Dz | Work Break Down Structure | Planning |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-14 | 2026-10-05 |  | false
ZPOiFhpKGEWv3OtfW9zKwmQAGGvc | Identify Risks | Planning |  | In progress | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-12 | 2026-10-08 |  | false
ByBTtul10Ui8_OYi3dvmSmQABMDk | Existing Environment Review | Design |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-08 | 2026-09-30 |  | false |  |  | 0/1 | Request Architecture from Customer
9TGtp_RsLk2CfeZ4sL5AcWQAJbM0 | Approve Solution Design | Design |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-11 | 2026-10-11 |  | false
2jAwaKJjMkK_Zwct-0l3R2QAK2b3 | Develop Solution | Execution |  | Completed | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-15 |  |  | false | 2026-10-07 | Emma Plimpton Liebowitz
30Zo2Z64i0OqfNwD_L1zj2QAMrI7 | Migrate Data | Execution |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-22 | 2026-10-15 |  | false
J8OAbVvxJ0Op6U4ammoM3mQABbWI | Complete Internal Validation | Execution |  | Not started | Low |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-28 | 2026-10-14 |  | false
xjBRPmEIQkqHj3DD8v66KmQALz0E | Execute Functional Testing | Testing |  | Not started | Medium | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-23 | 2026-10-02 |  | false
_fitm088ikaOJa6KkWd7JGQADa_B | Develop Test Plan | Testing |  | Not started | Important | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-09 | 2026-10-01 |  | false
-YwVHomytkimEoaWWCqRCmQAA_XJ | Resolve Defects | Testing |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-28 | 2026-10-13 |  | false
P3MWY1KufE6vaQ8xmeADc2QAEKN8 | Complete User Acceptance Testing | Testing |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-31 | 2026-10-15 |  | false
HzyYgF6mi0GdFVvjOp5kS2QALA9Y | Develop Deployment Plan | Deployment |  | In progress | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-10-28 |  |  | false
ffGst_jiCUmgKfXp2USlkGQAIlNI | Transition to Operations | Deployment |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-13 |  |  | false
C0Vqw_ydQkCw4NJVJO91B2QAI0dH | Finalize Project Artifacts | Closeout |  | Completed | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-16 |  |  | false | 2026-10-07 | Emma Plimpton Liebowitz
191PkDe6T0yL-9uBZqisXWQAK_xQ | Capture Lessons Learned | Closeout |  | Not started | Medium | Emma Plimpton Liebowitz | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-18 | 2026-11-15 |  | false
6jLcYpAxqUC0ZxOW4LeNHmQAJM6f | Obtain Customer Acceptance | Closeout |  | Not started | Urgent |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-21 | 2026-11-18 |  | false
AGTlvS15gU-GWuT607T53WQAE3aL | Project Closeout Meeting | Closeout |  | Not started | Medium |  | Emma Plimpton Liebowitz | 2026-10-07 | 2026-11-23 | 2026-11-23 |  | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
ts_u89-E4UioP7O4TbgE7WQANQft | Create Project Charter | UBJxZ0PTyUyGRksJNoU62GQADIne |  | Not started | Urgent | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-09 | 2026-09-29 |  | false
eI9R31SgOUyOfKsRr9BGsGQABWKX | Kickoff Meeting | UBJxZ0PTyUyGRksJNoU62GQADIne |  | Not started | Important |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-12 | 2026-11-12 |  | false |  |  | 0/1 | Deck generated
GnwBOY2jjkq32Fy2GaUWLGQAOxte | Architecture Diagram | woGWQZRTYkqcjMTNfU8jo2QAB-v1 |  | Not started | Medium | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-09 | 2026-10-07 |  | false |  |  | 0/3 | Final Review;Initial Draft;Comments Resolved
VUaPEzB-YkmOlP5sZO8I3GQAAIp- | Final Readiness Review | E0Zqce74c0uONrGKXj-HFmQACF2P |  | In progress | Medium | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-04 | 2026-11-07 |  | false
4aCd4U-ChEGCJnnDmQodR2QAEWxW | Identify Stakeholders | UBJxZ0PTyUyGRksJNoU62GQADIne |  | In progress | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-08 | 2026-09-27 |  | false
NX40UYKHtEiv71JIbz-EIGQAAgGz | Define Scope | UBJxZ0PTyUyGRksJNoU62GQADIne |  | Completed | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-10 |  |  | false | 2026-10-07 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241
3bzYQ5cZjEKjVbU74Swle2QAG3Dz | Work Break Down Structure | UBJxZ0PTyUyGRksJNoU62GQADIne |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-14 | 2026-10-05 |  | false
ZPOiFhpKGEWv3OtfW9zKwmQAGGvc | Identify Risks | UBJxZ0PTyUyGRksJNoU62GQADIne |  | In progress | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-12 | 2026-10-08 |  | false
ByBTtul10Ui8_OYi3dvmSmQABMDk | Existing Environment Review | woGWQZRTYkqcjMTNfU8jo2QAB-v1 |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-08 | 2026-09-30 |  | false |  |  | 0/1 | Request Architecture from Customer
9TGtp_RsLk2CfeZ4sL5AcWQAJbM0 | Approve Solution Design | woGWQZRTYkqcjMTNfU8jo2QAB-v1 |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-11 | 2026-10-11 |  | false
2jAwaKJjMkK_Zwct-0l3R2QAK2b3 | Develop Solution | 7ANXyqmcUkGyLgNZt8D3m2QAIEUl |  | Completed | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-15 |  |  | false | 2026-10-07 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241
30Zo2Z64i0OqfNwD_L1zj2QAMrI7 | Migrate Data | 7ANXyqmcUkGyLgNZt8D3m2QAIEUl |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-22 | 2026-10-15 |  | false
J8OAbVvxJ0Op6U4ammoM3mQABbWI | Complete Internal Validation | 7ANXyqmcUkGyLgNZt8D3m2QAIEUl |  | Not started | Low |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-28 | 2026-10-14 |  | false
xjBRPmEIQkqHj3DD8v66KmQALz0E | Execute Functional Testing | xzv4VVCjQEmoPThcdavXsGQAIN_V |  | Not started | Medium | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-23 | 2026-10-02 |  | false
_fitm088ikaOJa6KkWd7JGQADa_B | Develop Test Plan | xzv4VVCjQEmoPThcdavXsGQAIN_V |  | Not started | Important | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-09 | 2026-10-01 |  | false
-YwVHomytkimEoaWWCqRCmQAA_XJ | Resolve Defects | xzv4VVCjQEmoPThcdavXsGQAIN_V |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-28 | 2026-10-13 |  | false
P3MWY1KufE6vaQ8xmeADc2QAEKN8 | Complete User Acceptance Testing | xzv4VVCjQEmoPThcdavXsGQAIN_V |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-31 | 2026-10-15 |  | false
HzyYgF6mi0GdFVvjOp5kS2QALA9Y | Develop Deployment Plan | E0Zqce74c0uONrGKXj-HFmQACF2P |  | In progress | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-10-28 |  |  | false
ffGst_jiCUmgKfXp2USlkGQAIlNI | Transition to Operations | E0Zqce74c0uONrGKXj-HFmQACF2P |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-13 |  |  | false
C0Vqw_ydQkCw4NJVJO91B2QAI0dH | Finalize Project Artifacts | vuCP27qC3EWelE5sQmWGtGQALQh6 |  | Completed | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-16 |  |  | false | 2026-10-07 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241
191PkDe6T0yL-9uBZqisXWQAK_xQ | Capture Lessons Learned | vuCP27qC3EWelE5sQmWGtGQALQh6 |  | Not started | Medium | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-18 | 2026-11-15 |  | false
6jLcYpAxqUC0ZxOW4LeNHmQAJM6f | Obtain Customer Acceptance | vuCP27qC3EWelE5sQmWGtGQALQh6 |  | Not started | Urgent |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-21 | 2026-11-18 |  | false
AGTlvS15gU-GWuT607T53WQAE3aL | Project Closeout Meeting | vuCP27qC3EWelE5sQmWGtGQALQh6 |  | Not started | Medium |  | 9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | 2026-10-07 | 2026-11-23 | 2026-11-23 |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
UBJxZ0PTyUyGRksJNoU62GQADIne | Planning
woGWQZRTYkqcjMTNfU8jo2QAB-v1 | Design
7ANXyqmcUkGyLgNZt8D3m2QAIEUl | Execution
E0Zqce74c0uONrGKXj-HFmQACF2P | Deployment
xzv4VVCjQEmoPThcdavXsGQAIN_V | Testing
vuCP27qC3EWelE5sQmWGtGQALQh6 | Closeout

## Users
User ID | User Name | Email
9bc61855-b6b4-46eb-8aa6-bfbc79e4d241 | Emma Plimpton Liebowitz | eplimpton@esri.com